### department of Health

Dr. Alicia Pointer, DO, MPH, FAAP

Commissioner of Health

124 Main Street

Goshen, New York  10924

Commissioner/Administration	(845) 291-2332

Nursing	(845) 291-2330

Environmental Health	(845) 291-2331

Early Intervention	(845) 360-6630

Fax: (845) 360-9076

www.orangecountygov.com

Steven M. Neuhaus

##### County Executive

Orange County Early Intervention

PLAN AND TIMELINE FOR TRANSITION FROM NYEIS TO THE EI HUB

9/4/2024

This document outlines operational changes in the Orange County Early Intervention Program for the period September 30 to October 14, 2024.

The timelines are as follows:

- September 30 – October 4 (1 business week) to resolve outstanding issues in NYEIS

- October 7- October 14 (1 business week) without access to either NYEIS or the EI Hub

- October 15, the EI Hub will go live and become the system for all Early Intervention case management.  NYEIS will be available in a read-only state. Information in NYEIS and attachments can be viewed, printed out, and downloaded. No data entry can be made.

Orange County EI Transition Plan Overview

All child cases will be migrated from NYEIS to the EI Hub, and the New York State Department of Health, Bureau of Early intervention (NYS BEI) and Public Consulting Group (PCG) have done extensive testing to ensure that the data migrated is complete and accurate.  However, we will work with the provider community to ensure that tasks and actions ARE NOT pending resolution at the time of transition, since EI Hub processes are structured differently than NYEIS.  Thus, we seek to resolve all referrals, multidisciplinary evaluations, IFSPs, service issues, transfers, closures, and any other tasks by the time NYEIS goes offline on Friday, October 4.

The document below explains each step of the process, and clearly defines the role of providers in facilitating case resolution in NYEIS and resumption of activities in the EI Hub.  This includes the period of September 30 - October 14, when new submissions to Orange County will stop to allow first for NYEIS close-out, and then for a week of no access to either system.

Provider Preparation for the EI-Hub

For providers, the EI Hub changes not only case processing, but many administrative functions.  Providers must review the transition planning resources available on the PCG Learning Management System EI-Hub Launch Transition Resources page.  Resources include, The EI-Hub Transition Resource List for Agencies, and The EI-Hub Transition Resource List for Individual Providers.  That document includes a visual timeline of the cutover period for each of NYEIS, EI Hub, and EI Billing. The EI-Hub Transition Resource List document addresses each element of the Early Intervention programmatic process as well as billing, provider credentials and approvals, and employee/contractor management.

Provider agencies must act now to update their Employee/Contractor list in NYEIS and make sure that it includes everyone on their staff who may need to access the EI Hub for any reason.  Everyone with a Provider Agreement, basic or appendix, will need an HCS account and access to the EI Hub.  Ensuring that Employee/Contractor lists are up to date will reduce the amount of work that providers will have to do in the EI Hub to set up roles.

Agencies must also make sure that they have identified at least one EI Hub Role Administrator. Please ensure that your designated Role Administrator understands the EI Hub user roles, which are different from NYEIS roles; and that they have identified which role(s) each user will need.  NYEIS users will be migrated to the EI Hub with a single role roughly equivalent to their role in NYEIS, but agencies may find that they need additional roles due to the differences in the systems.  Role Administrators will be responsible for assigning those additional roles when the EI Hub goes live. The county will no longer be able to assign user roles for providers.

Note that EI Billing user roles will not be migrated, and Role Administrators will need to configure accounts for anyone who needs access to EI Billing.  There are helpful tools in the  Learning Management System.

Attached to this plan, please find some resources for your convenience:

- EI-Hub User Roles - Crosswalk of EI-Hub Component and NYEIS User Roles

- Case Management User Roles Job Aid

- The EI-Hub Transition Resource List for Agencies

- The EI-Hub Transition Resource List for Individual Providers

It is recommended that agencies and providers start increasing their billing frequency, so that the impact of EI Billing being down, and payments being paused does not have as much of an impact on cash flow.  October 4th is the last day to work claims in NYEIS until after the EI Hub goes live on October 15th.  Final payments for claims from the last NYEIS file will be made the week of October 7th, resuming the following week of October 15th.

Orange County EI Transition Plan Sections

- Referrals

- Multidisciplinary Evaluations and Initial Individualized Family Service Plan (IFSP) Meetings

- Ongoing IFSPs

- Amendments and Service Changes

- Tasks and Closures

- Transition to CPSE

- Transfers

- New NYEIS Accounts

| - REFERRALS |  |  |
| --- | --- | --- |
| Date | Providers | Orange County |
| Wed, October 2 | - Last day to submit referrals through NYEIS | - Last day to accept new referrals through NYEIS for immediate processing. |
| Wed, October 2 – Fri, October 4 | - Fax all new referrals: no referrals submitted in NYEIS - Promptly accept all OSC assignments to ensure service authorizations are resolved before the cutover. | - Processes all referrals and assigns ISC/EIOD |
| Mon, October 7-Fri, October 11 (Blackout Period, Oct 7 – Oct 14: No NYEIS or EI Hub Access) | - Continue to fax all new referrals | - Continue to process all referrals and assigns ISC/EIOD |
| Tues, Oct 15 (EI Hub Go-Live) | - Continue to submit referrals via fax - Providers must ensure that they are retaining the referral forms sent to the county as part of their child record. | - Begins processing all referrals received in the EI Hub |
| - MULTIDISCIPLINARY EVALUATIONS (MDEs) AND INITIAL IFSP MEETINGS |  |  |
| Date | Providers | Orange County ISC/EIOD |
| Wed, October 2 | - Last day to submit eligible and ineligible MDEs | - Last day to accept eligible and ineligible MDEs |
| Mon, Sep 30 - Fri, Oct 11 (Includes the Blackout Period, Oct 7 – Oct 14: No NYEIS or EI Hub Access) | - Fax all eligible and ineligible MDEs - Evaluation agencies keep track of any cases in which an MDE is completed but was not submitted by Oct 2. They will need to follow up on those cases in the EI Hub on Tuesday, Oct 15. | - Processes all MDEs that were submitted by Friday, Sept 30, and schedules initial IFSP meetings - Keep track of any cases in which an MDE is completed but was not submitted by Sept 30 - Create paper IFSPs and fax them to the OSC agency |
| Tues, Oct 15-Friday, Oct 18 (EI Hub Go-Live) | - Evaluation agencies inform Service Coordinators of children whose MDEs have been completed and are ready for submission - Evaluation agencies who receive service authorizations submit MDEs in the EI Hub Note: Any MDE that was not submitted in NYEIS by Sept 30 must be submitted in the EI Hub. To submit an MDE, the ISC must first draft a service authorization, the EIOD must approve it, and the evaluation agency must accept it. Detailed revised Policy and Procedure forthcoming. | - Initial Service Coordinators create MDE service authorizations in the EI Hub - EIOD reviews and approves MDE service authorizations - Receives, reviews, and accepts MDEs submitted by evaluation agencies |
| - ONGOING IFSPs |  |  |
| Date | Providers | Orange County EIOD |
| Mon, Sept 9 -Fri, Oct 4 | - Service Coordinators and provider agencies identify all IFSPs that will be ending between Sept 9 and Oct 4 and: - Submit all IFSPs prior to their expiration date to be processed in NYEIS | - Process all review and annual IFSPs that expire between Sept 9 and Oct 4 as follows: - Hold meetings as needed |
| Mon, Sept 30-Fri, Oct 4 | - Work with the EIOD to provide any information needed to resolve IFSP/service issues in NYEIS and notify parents of determinations. | - Resolve any outstanding IFSP/service issues in NYEIS |
| Mon, Oct 7-Fri, Oct 11 (Blackout Period, Oct 7 – Oct 14: No NYEIS or EI Hub Access) | - OSC work with EIOD to schedule IFSP meetings - Facilitate IFSP meetings on paper. Fax to the EIOD | - Continue to schedule initial and ongoing IFSP meetings |
| Tues, Oct 15 | - OSCs business as usual | - ISC/EIODs resumes business as usual |
| - AMENDMENTS AND SERVICE CHANGES |  |  |
| Date | Providers | Orange County EIOD |
| Fri, Oct 4 | - Last day to submit amendments and service modification requests, including assistive technology (AT) and evaluation requests. | - Last day to accept amendments and service modification requests, including AT and evaluation requests. |
| Mon, Sept 30-Fri, Oct 4 | - OSCs work with the EIODs to provide any information needed to resolve amendments and service modification requests in NYEIS | - Resolves all submitted (pending) amendments and service modification requests in NYEIS, including AT and evaluation. |
| Mon, Oct 7-Fri, Oct 11 (Blackout Period, Oct 7 – Oct 14: No NYEIS or EI Hub Access) | - OSCs keep a log of all amendment, service modification and evaluation requests for submission in the EI Hub on Oct 15. | - Informs anyone who contacts the EIOD regarding an amendment, service modification, AT request, or evaluation request that the request must be submitted in the EI Hub on Oct 15. |
| Tues, Oct 15 | - Resume submitting amendments and service modification requests in the EI Hub | - Resumes acceptance and processing of amendments, service modification, and AT and evaluation requests. |
| - TASKS AND CLOSURES |  |  |
| Date | Providers | Orange County EIOD |
| Mon, Sept 30-Fri, Oct 4 | - Follows up timely with the CMA Help Desk if needed regarding outstanding tasks | - Clear all task queues in NYEIS and informs providers if they need to follow up with CMA regarding outstanding tasks |
| Mon, Oct 7-Fri, Oct 11 (Blackout Period, Oct 7 – Oct 14: No NYEIS or EI Hub Access) | - OSCs continue to complete closure forms and obtain parent consent. - OSCs keep a log of all pending closures for submission in the EI Hub on Oct 15. | - Informs anyone who contacts the EIOD regarding closure that requests will be accepted on Oct 15. |
| Tues, Oct 15 | - Follow detailed revised Policy and Procedures (forthcoming). | - Resumes processing all case actions, including closures |
| - TRANSITION |  |  |
| Date | Providers | Orange County EIOD |
| Mon, Sept 30-Fri, Oct 4 | - OSCs notify EIOD immediately if a child on their caseload requires an IFSP meeting or need to extend services during this time period due to impending age-out. | - Ensures all cases are resolved |
| - TRANSFERS |  |  |
| Date | Providers | Orange County EIOD |
| Fri, Sept 27 | - Last day to transfer children across counties | - Last day to accept transfers from other counties - Last day to initiate transfers across counties |
| Mon, Sept 30-Fri, Oct 4 | - OSCs keep a log of all transfer requests for submission in the EI Hub on Oct 15 - OSCs work with the EIOD regarding the transferring of cases. | - Facilitates transfers received on or before Sept 27 - Convenes IFSP meetings for transfer requests received on or before Sept 27 |
| Mon, Oct 7-Fri, Oct 14 (Blackout Period, Oct 7 – Oct 14: No NYEIS or EI Hub Access) | - OSCs keep a log of all transfer requests for submission in the EI Hub on Oct 15. | - Informs anyone who contacts the county regarding transfer that the transfer request will be held until Oct 15. |
| Tues, Oct 15 | - Begin submitting transfer requests | - Facilitates transfers as requested |
| - NYEIS ACCOUNTS |  |  |
| Date | Providers | Orange County |
| Wed, Oct 2 | - Last day to request a new NYEIS account | - Last day to accept new NYEIS account requests. |
| Tues, Oct 15 | - Will be able to manage their own accounts in the EI Hub | - Only manages and issues Orange County EI Hub accounts. |